## Slide 1: Time and Cost Management of Nablus City Mall
Prepared by: Ghalib Al-Shaikh,
Mahmoud Awad,
Osama Kolayb,
Sa’ed Turkman,
Under Supervision of: Eng. Reema Nassar.

## Slide 2
Outline
Part 1: Introduction,
Part 2: Objectives,
Part 3: Project Description,
Part 4: Quantities Surveying Using Revit Software,
Part 5: Project Human Resources Management,
Part 6: Resources Price,
Part 7: Project Scope Management,
Part 8: Time and Cost Management Using
Part 9: Cost and Price Estimate.
Primavera Software,

## Slide 3
Introduction
Estimating is an approximation that defines the Cost of construction Activity or activities prior to commencement of work V.S the cost of work during and after construction, which is the Actual cost.
Estimating is not exact science. It is group of skills and experience in knowledge of construction , knowledge of prices, Common sense, the judgment required
An estimate is the “Prediction” of future construction costs.
PART 1

## Slide 4
Introduction
  Project Management: is the sum of all activities such as Planning, organising, implementing and controlling a project in order to meet the client’s expectation from start to finish within the planned period, budget and quality.
PART 2

## Slide 5
Objectives
We have two main objectives for this project:
Calculate the budgeted cost and price for foundation, structural elements, partitions, stone and plastering after estimated the quantities takeoff for it.
Calculate the optimal period needed to finish works by depending on productivity rate for resources (labors and equipment).

## Slide 6: Project Description
This report deals with time and cost management of Nablus City Mall in Nablus, which has a location of 32° 13’ 25˝ N, 35° 15’ 27˝ E, and about 600 m above mean sea level. The mall consists of fourteen floors with a total area of 35557 m².
The building is multifunctional structure and table 1.2.1 summarizes the functions, area and height of each story center to center.
PART 3

## Slide 7
Function | High (m) | Area (m²) | Floor Number
Garages | 3.35 | 3017.20 | B4
Shopping | 3.50 | 2723.40 | B3
Shopping | 4.00 | 2521.00 | B2
Shopping | 3.80 | 2422.00 | B1
Shopping | 3.95 | 2550.80 | Ground Floor
Shopping | 3.75 | 2550.80 | F1
Offices | 3.50 | 2565.00 | F2
Offices | 3.00 | 2544.80 | F3
Offices | 3.30 | 2530.50 | F4
Offices | 3.30 | 2530.50 | F5
Offices | 3.30 | 2530.50 | F6
Garages | 3.30 | 2530.50 | F7
Garages | 3.30 | 2276.00 | F8
Garages | 3.30 | 2176.30 | F9
- | 2.65 | 87.24 | Stair Floor

## Slide 11
Quantities Surveying Using
Revit Software
PART 4

## Slide 12: Quantities Surveying Using Revit Software
Levels Definition in Revit
Floor Number | High (m)
B4 | 3.35
B3 | 3.5
B2 | 4
B1 | 3.8
Ground Floor | 3.95
F1 | 3.75
F2 | 3.5
F3 | 3
F4 | 3.3
F5 | 3.3
F6 | 3.3
F7 | 3.3
F8 | 3.3
F9 | 3.3
Stair Floor | 2.65
Quantities Surveying Using
“Revit Software”

## Slide 13: Link CAD Importing for Drawing

## Slide 14: Sections Definition for the Structural Elements
Column Section Definition Example
Beam Section Definition Example
Shear Wall Section Definition Example
Floor Section Definition Example
Sections Definition for the Structural Elements

## Slide 15: Sections Definition for non-Structural Elements
Partition Wall Definition Example
Stone Wall Definition Example
Sections Definition for non-Structural Elements

## Slide 16: Drawing Stages
Raft Draw Example for Block 3
Rectangular Column Draw Example

## Slide 17
Beams Draw Example for Block 2
Ribs Draw Example for Block 3

## Slide 18
Cover Slab Draw Example for Block 3

## Slide 19
Partition walls Draw Example for Block 1

## Slide 20
Stone Walls Draw Example for Block 3

## Slide 21: 3-D View for Block 1

## Slide 22: Top View for Block 1

## Slide 23: 3-D View for Block 2

## Slide 24: Top View for Block 2

## Slide 25: 3-D View for Block 3

## Slide 26: Top View for Block 3

## Slide 27: Drawing Reinforcement Using Revit
Steel Bars Distribution for the Raft in Revit

## Slide 28: Slide Title
Rebar Extension for Columns

## Slide 29: Columns Rebar in Revit
Bars distribution for rectangular and circular columns in Revit

## Slide 30: Slide Title
Rebar Extension for Shear Walls

## Slide 31: Shear Walls Rebar in Revit
Bars Distribution for Shear Walls in Revit

## Slide 32: Slide Title
Rebar Extension for Beams

## Slide 33: Beams Rebar in Revit
Bent Bars Distribution for Beams in Revit
Bars and stirrups distribution for Beams in Revit

## Slide 34: Slabs Rebar in Revit
Bars Distribution for Ribs in Revit

## Slide 35
Bars Distribution for Shrinkage Steel Area in Revit

## Slide 36: Slide Title

## Slide 38
Columns Schedules Example

## Slide 39: Slide Title
Shear Walls Schedules Example

## Slide 40
Beams Schedules Example

## Slide 41
Floors Schedules Example

## Slide 42
Stairs Schedules Example

## Slide 43
Stones and Partitions Schedules Example

## Slide 44
Formwork Schedules Example

## Slide 45
Project Human Resources
Management
PART 5

## Slide 46
Actual Resource Needed in the Project |  | 
Num. of persons | Work Type | Equivalent Crews Number
6 | Carpenter | 3
3 | HELPER (carpenter) | 
4 | steel fixer for column | 4
12 | steel fixer for raft | 12
8 | steel fixer for floor | 8
1 | Mason (stones) | 1
1 | HELPER (stones) | 
4 | Mason (partitions) | 4
4 | HELPER (partitions) | 
6 | Mason (plaster) | 6
6 | HELPER (plaster) | 

## Slide 48
Resources Price
Labor Resources Price |  | 
Resource Name | Price / Unit | Unit
Carpenter | 200 | Nis/d
Helper with Carpenter | 100 | Nis/d
Steel Fixer for Floors | 225 | Nis/d
Steel Fixer for Columns and Shear Walls | 225 | Nis/d
Mason for Stone Works | 560 | Nis/d
Helper for Stone Works | 200 | Nis/d
Mason for Partitions Works | 360 | Nis/d
Helper for Partitions Works | 85 | Nis/d
Mason for Plastering Works | 768 | Nis/d
Helper for Plastering Works | 85 | Nis/d
PART 6

## Slide 49
Resources Price
Materials Prices |  | 
Resource Name | Price / Unit | Unit
Concrete B300 | 320 | Nis/CM
Concrete B500 | 400 | Nis/CM
Steel 420 Mpa | 2600 | Nis/Ton
Stone | 130 | Nis/m²
Block 10 cm | 1.5 | Nis/Unit
Block 15 cm | 2 | Nis/Unit
Block 20 cm | 2.5 | Nis/Unit
Block 24 cm for Slabs | 2.8 | Nis/Unit
Mortar for Partition Works | 260 | Nis/CM
Plain Concrete | 270 | Nis/CM
Plastering Materials | 10 | Nis/m²

## Slide 50
Project Scope Management
PART 7

## Slide 51: Slide Title
Work Breakdown Structure(WBS)

## Slide 52
Columns Works Duration and Materials needed for Block 1
Columns Works for Block 1 |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
 |  | B4 | B3 | B2 | B1 | GF | F1 | F2 | F3 | F4 | F5 | F6 | F7 | F8 | F9
Formwork for columns | D | 1.75 | 1.75 | 2 | 2 | 2 | 2 | 1.75 | 2 | 1.75 | 1.75 | 1.75 | 1.75 | 1.75 | 1.75
 | M | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Steel fixing for columns | D | 1.25 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
 | M | 3520 | 2535 | 2870 | 2740 | 2830 | 2720 | 2560 | 2810 | 2450 | 2450 | 2450 | 2450 | 2450 | 2450
Casting concrete for columns | D | 0.25 | 0.25 | 0.25 | 0.25 | 0.25 | 0.25 | 0.25 | 0.25 | 0.25 | 0.25 | 0.25 | 0.25 | 0.25 | 0.25
 | M | 19 | 20 | 23 | 22 | 22 | 22 | 20 | 22 | 19 | 19 | 19 | 19 | 19 | 19
Deshuttering for columns | D | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5
 | M | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Curing for columns | D | 14 | 14 | 14 | 14 | 14 | 14 | 14 | 14 | 14 | 14 | 14 | 14 | 14 | 14
 | M | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0

## Slide 53
Shear walls Works
Shear Walls works for Block 1 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
 |  | B4 | B3 | B2 | B1 | GF | F1 | F2 | F3 | F4 | F5 | F6 | F7 | F8 | F9 |  | 
Formwork for walls | D | 4 | 4.25 | 5 | 4.75 | 1.75 | 1.75 | 1.5 | 1.75 | 1.5 | 1.5 | 1.5 | 1.5 | 1.5 | 1.5 |  | 
 | M | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 
Steel fixing for walls | D | 2.75 | 2.5 | 2.75 | 2.75 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 |  | 
 | M | 10650 | 9670 | 10940 | 10445 | 3870 | 3700 | 3440 | 3850 | 3280 | 3280 | 3280 | 3280 | 3280 | 3280 |  | 
Casting concrete for walls | D | 0.75 | 0.75 | 0.75 | 0.75 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 |  | 
 | M | 78 | 81 | 94 | 89 | 37 | 35 | 33 | 37 | 31 | 31 | 31 | 31 | 31 | 31 |  | 
Deshuttering for walls | D | 1.5 | 1.5 | 1.75 | 1.75 | 0.75 | 0.75 | 0.5 | 0.75 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 |  | 
 | M | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 
Curing for walls | D | 14 | 14 | 14 | 14 | 14 | 14 | 14 | 14 | 14 | 14 | 14 | 14 | 14 | 14 |  | 
 | M | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 

## Slide 54
Stone Works
Stone works for Block 1 |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
 |  | B4 | B3 | B2 | B1 | GF | F1 | F2 | F3 | F4 | F5 | F6 | F7 | F8 | F9
Parameter Slab Stone installation | D | 0 | 0 | 0 | 0 | 0 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3
 | M | 0 | 0 | 0 | 0 | 0 | 24 | 24 | 24 | 24 | 24 | 24 | 24 | 24 | 24
External walls stone installation | D | 0 | 0 | 0 | 0 | 4 | 3.75 | 3.5 | 4 | 3.25 | 3.25 | 3.25 | 3.25 | 3.25 | 3.25
 | M | 0 | 0 | 0 | 0 | 32 | 30 | 28 | 31 | 26 | 26 | 26 | 26 | 26 | 26

## Slide 55
Floors Works for Block 1 |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
 |  | B4 | B3 | B2 | B1 | GF | F1 | F2 | F3 | F4 | F5 | F6 | F7 | F8 | F9
Formwork for floors | D | 5.25 | 4.75 | 4.25 | 4.25 | 4.25 | 4.25 | 4.25 | 4.25 | 4.25 | 4.25 | 4.25 | 4.25 | 4.25 | 4.25
 | M | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Blocks distribution on the floors | D | 1.25 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
 | M | 4050 | 3640 | 3310 | 3310 | 3310 | 3310 | 3310 | 3310 | 3310 | 3310 | 3310 | 3310 | 3310 | 3310
Steel fixing for beams | D | 4.75 | 5 | 4.75 | 4.5 | 4.75 | 4.75 | 4.75 | 4.75 | 4.75 | 4.75 | 4.75 | 4.75 | 4.75 | 4.75
 | M | 8280 | 8650 | 8140 | 7950 | 8500 | 8430 | 8430 | 8430 | 8430 | 8430 | 8430 | 8430 | 8430 | 8340
Steel fixing for Ribs | D | 1.75 | 1.25 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
 | M | 4590 | 3260 | 2320 | 2320 | 3210 | 3210 | 3210 | 3210 | 3210 | 3210 | 3210 | 3210 | 3210 | 3210
Steel fixing for the shrinkage mesh | D | 0.75 | 0.75 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5
 | M | 1880 | 1680 | 1530 | 1530 | 1530 | 1530 | 1530 | 1530 | 1530 | 1530 | 1530 | 1530 | 1530 | 1530
Casting concrete for the floors | D | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
 | M | 155 | 142 | 154 | 142 | 145 | 150 | 150 | 150 | 150 | 150 | 150 | 150 | 150 | 150
Curing for floors | D | 28 | 28 | 28 | 28 | 28 | 28 | 28 | 28 | 28 | 28 | 28 | 28 | 28 | 28
 | M | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
DE shuttering for floors | D | 1.25 | 1.25 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
 | M | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0

## Slide 56
Partition Walls Works
Partition Walls Installation for Block 1 |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
 |  | B4 | B3 | B2 | B1 | GF | F1 | F2 | F3 | F4 | F5 | F6 | F7 | F8 | F9
Partition walls of block 10 cm | Duration | 0 | 0.25 | 0.25 | 0 | 0 | 0.25 | 0.25 | 1 | 2.25 | 2.25 | 2.25 | 0 | 0 | 0
 | Area | 0 | 23 | 27 | 0 | 0 | 29 | 25 | 77 | 213 | 213 | 212 | 0 | 0 | 0
Partition walls of block 15 cm | Duration | 0.5 | 2.25 | 2.25 | 1.25 | 3 | 1.75 | 1.5 | 2 | 2 | 2 | 2 | 1 | 1 | 0.5
 | Area | 48 | 200 | 212 | 128 | 288 | 153 | 139 | 188 | 179 | 179 | 179 | 87 | 87 | 44
Partition walls of block 20 cm | Duration | 0 | 0.25 | 0.25 | 0.25 | 0.25 | 0.25 | 0.25 | 0.25 | 0.25 | 0.25 | 0.25 | 0 | 0 | 0
 | Area | 0 | 10 | 11 | 11 | 11 | 12 | 10 | 12 | 11 | 11 | 10 | 0 | 0 | 0

## Slide 57
Plastering Walls Works
Plastering for Block 1 |  |  |  |  |  |  |  |  |  |  |  |  |  | 
 | B4 | B3 | B2 | B1 | GF | F1 | F2 | F3 | F4 | F5 | F6 | F7 | F8 | F9
Shear Wall | 750 | 670 | 610 | 610 | 610 | 610 | 610 | 610 | 610 | 610 | 610 | 610 | 610 | 610
Floor | 674 | 708 | 821 | 776 | 289 | 273 | 253 | 285 | 237 | 237 | 237 | 237 | 237 | 237
Wall (10cm) | 0 | 46 | 54 | 0 | 0 | 58 | 50 | 154 | 426 | 426 | 426 | 0 | 0 | 0
Wall (15cm) | 96 | 400 | 424 | 256 | 576 | 306 | 278 | 376 | 358 | 358 | 358 | 174 | 174 | 88
Wall (20cm) | 0 | 20 | 22 | 22 | 22 | 24 | 20 | 24 | 22 | 22 | 20 | 0 | 0 | 0
Area | 1520 | 1844 | 1931 | 1664 | 1497 | 1271 | 1211 | 1449 | 1653 | 1653 | 1651 | 1021 | 1021 | 935
Duration | 4.00 | 5.00 | 5.00 | 4.50 | 4.00 | 3.50 | 3.25 | 3.75 | 4.50 | 4.50 | 4.50 | 2.75 | 2.75 | 2.50

## Slide 58
Time and Cost Management Using
Primavera Software
PART 8

## Slide 59
Project Definition In Primavera

## Slide 60
Calendar Definition

## Slide 61
Currency Definition

## Slide 62
Work Breakdown Structure
(WBS) Assignment

## Slide 63
Activities Definition

## Slide 64
Activities Relationships Assignment

## Slide 65
Resources Definition

## Slide 66
Resources Assignment

## Slide 67
Schedule (Run)

## Slide 68
Results from Primavera for the Planning Phase
- Time schedule report .
- Budgeted total cost reports.
- Gantt chart found sheets.
- S-curve sheets.

## Slide 69
Time Schedule Report

## Slide 70
Budgeted Total Cost Reports

## Slide 72
Gantt chart found sheets

## Slide 73
S-Curve found sheets

## Slide 74
S-Curve

## Slide 75
Cost and Price Estimate
PART 9

## Slide 76
Direct Cost
The direct cost calculated by Revit and primavera software and it was 13,530,715 NIS.

## Slide 77
Job overhead cost = 10%
Operating overhead cost = 5%
Profit = 15%
Waste factor for materials = 5%
Waste of mortar in plastering = 13%
Materials Waste Factors
In-Direct
Cost

## Slide 78
Blinding and Raft Foundation Cost and Price
1- Blinding direct cost = Budgeted Material cost + Budgeted Labor cost
= 97,600 + 2,625
= 100,225 NIS
2 – Raft Foundation direct cost = Budgeted Material cost + Budgeted Labor cost
= 1,672,000 + 77,625
= 1,749,625 NIS
Budgeted Total direct Cost of the Foundation = 1,849,850 Nis
Indirect cost = (0.1+0.05) ☓1,849,850
= 277,478 NIS
Waste of the materials = 0.05☓ (1,672,000 + 97,600)
= 88,480 NIS
Budgeted Total cost = 1,849,850 + 277,478 + 88480
= 2,215,808 NIS

## Slide 79
Price of the foundation = 2,215,808 + (0.15☓2,215,808)
= 2,548,179 NIS
=
=

## Slide 80
Columns and Shear Walls Cost and Price
Columns and Shear Walls direct cost =
=
=
Indirect cost = 0.15☓2,648,632.69
= 397,294.9 NIS
Waste of the materials = 106,109 NIS
Budgeted Total cost = 2,648,632.69 + 397,294.9 +106,109
= 3,152,037 NIS

## Slide 81
Price of the columns and shear wall = 3,152,037 + (0.15☓3,152,037)
= 3,624,843 NIS
=
= 3,580 NIS/m³

## Slide 82
Floors cost and price
Floors direct cost = Budgeted Material cost + Budgeted Labor cost
= 5,195,690 + 920,475
= 6,116,165 Nis
Indirect cost = 0.15☓6,116,165
= 917,424.75 Nis
Waste of the materials = 0.05☓5,195,690
= 259,785
Budgeted Total Cost = 6,116,165 + 917,424.75 + 259,785
= 7,293,385 Nis

## Slide 83
Price of the floors = 7,293,385 + (0.15☓7,293,385)
= 8,387,393 NIS
=
= 1000 NIS/m³

## Slide 84
Partitions Cost and Price
Partitions direct cost = Budgeted Material cost + Budgeted Labor cost
= 334,195 + 249,200
= 583,395 NIS
Indirect cost = 0.15☓583,395
= 87,509.25 NIS
Waste of the materials = 0.05☓334,195
= 16,710 NIS
Budgeted Total cost = 583,395 + 87,509.25 + 16,710
= 687,614.25 NIS

## Slide 85
Price of the partitions = 687,614.25 + (0.15☓687,614.25)
= 790,756.39 NIS
=
= 61 NIS/m²

## Slide 86
Stone Works Cost and Price
Stone Works direct cost = Budgeted Material cost + Budgeted Labor cost
= 322,136 + 213,750
= 535,886 NIS
Indirect cost = 0.15☓535,886
= 80,383 NIS
Budgeted Total cost = 535,886 +80,383
= 616,269 NIS
Price of the Stone works = 616,269 + (0.15☓616,269)
= 708,709 NIS
= = 319 NIS/m²

## Slide 87
Plastering Cost and Price
Plastering direct cost = Budgeted Material cost + Budgeted Labor cost
= 762,950 + 1,033,836
= 1,796,786 Nis
Indirect cost = 0.15☓1,796,786
= 269,518 Nis
Waste of the materials = 0.13☓762,950
= 87,484 Nis
Budgeted total cost of the plastering = Budgeted Material cost + Budgeted Labor cost
= 1,796,786 + 269,518 + 87,484
= 2,153,788 Nis

## Slide 88
Price of the plastering = 2,153,788 + (0.15☓2,153,788)
= 2,476,856 NIS
=
= 32.1 NIS/m²

## Slide 89
B.O.Q. |  |  |  |  | 
Activity Name | Quantity |  | Unit Price |  | Total Price
 | Value | Unit | Value | Unit | 
Blinding and Raft Foundation | 3,982.97 | m³ | 640 | NIS/ m³ | 2,548,179
Columns and Shear Walls | 10,012.7 | m³ | 3,580 | NIS/ m³ | 3,624,843
Floors | 8,386 | m³ | 1000 | Nis/ m³ | 8,387,393
Partitions | 12,960 | m² | 61 | Nis/m² | 790,756
Stone Works | 2225 | m² | 319 | Nis/m² | 708,709
Plastering | 77,143 | m² | 32.1 | Nis/m² | 2,476,856
 |  |  |  | Total Price | 18,536,736 Nis
Bill of Quantity “B.O.Q.’’

## Slide 90
Results
The total project cost is 13,530,715 NIS.
The total project price is 18,536,736 NIS.
The project planning start at 1st Jan, 2018, and the planned finish date is 22th March 2020.
4. The duration for the project is 818 calendar days and 696 working days.
5. The cost Distribution and Percentages in the following table:

## Slide 91
Item | Total Cost | Total Price | Percent % of Total
Blinding and Raft Foundation | 2,215,808 | 2,548,179 | 14%
Columns and Shear Walls | 3,152,037 | 3,624,843 | 20%
Floors | 7,293,385 | 8,387,393 | 45%
Partitions | 687,614 | 790,756 | 4%
Stone Works | 535,886 | 708,709 | 4%
Plastering | 2,153,788 | 2,476,856 | 13
Summation ($) | 16,038,518 | 18,536,736 | 100%
Cost Distribution and Percentage