## Slide 1: Time and cost assessment of Ministry of Local Government In The City Of Ramallah
Prepared by:
Mohammad Abusa’a
Sadeq Yasin
Ayman Majdi
Yazan Qasem
Supervisor:
Eng Reema Bdair

## Slide 2: Presentation content
Introduction.
Case Study.
Purpose of the study.
Methodology.
Work breakdown structure.
Quantity survey.
Cost Estimation.
Time scheduling.
Results and Conclusion.

## Slide 3: Introduction
Project Management
Pros of applying project management on the construction projects

## Slide 4: Case study
Ministry of local government in Ramallah city.
Building Consist of 9 Floors.
Total area of the building: 7000 square meter.

## Slide 5: CASE STUDY
Started at 2015/4/28.
Total cost of the project was 2,512,523 $.
Type of contract: Unit price.

## Slide 6: Purpose of study
Apply management principles to assets the project by the terms of time and cost.

## Slide 7: Methodology
Site visiting
Collect information.
Primavera
Time estimation.
Revit
Quantity survey.

## Slide 8: methodology
Revit architectural model
Reality

## Slide 9: Work break down structure
It was developed according to the bell of quantity.

## Slide 10: Work break down structure

## Slide 11: Quantity survey
Slabs concrete volume

## Slide 12: Quantity survey
Beams concrete volume

## Slide 13: Quantity survey
Reinforcement steel quantities.

## Slide 14: Quantity survey
Reinforcement steel quantities for beams.

## Slide 15: Quantity survey
Walls concrete volume.

## Slide 16: Quantity survey
Columns concrete volume.

## Slide 17: Quantity survey
Reinforcement steel quantities for walls.

## Slide 18: Quantity survey
Reinforcement steel quantities for columns.

## Slide 19: Quantity survey
Foundations concrete volume.

## Slide 20: Quantity survey
Reinforcement steel quantities in general.

## Slide 21: Cost estimation
Direct cost.
+ Job overhead (%)
+ Overhead (%)
Total Price

## Slide 22: DIRECT COST
Direct cost =

## Slide 23: Job overhead

## Slide 24: Overhead
(DC+JO%)*(1+OH%)

## Slide 25: TOTAL PRICE
(DC+JO%+OH%)*(1+Profit%)

## Slide 26: Time scheduling
Estimate activities duration.
Insert activities into P6
Estimate project total duration.

## Slide 27: ACTIVITIES DURATION
Activities duration have been taken from the contractor.

## Slide 28: P6 Activities

## Slide 29: Total duration of the project
Project total duration= 449 working days

## Slide 30: Result
Study results:
Project Duration is 449 Working days
Project Total Price =2,685,979 $

## Slide 31: Comparison
Study time and cost:
Project duration = 449 working days
Project total price=2,685,979 $
Actual time and cost:
Project duration=635 working days
Project total price=2,512,523 $

## Slide 32: Comparison
635-499=136 working days
= 2,685,979 $ - 2,512,523 $ = 173,456 $
Cost Difference
Delay in project

## Slide 33: Recommendations
As a result of wrong site investigation and lack of information about the soil, a 135 days of delay occurred.
All Crashing.