## Slide 1: Assessment of the Ministry of Public Works and Housing Building (Quantity Surveying And Cost Estimating)
Prepared By: Abdullah Aqra
Jad Majed Al-Zagal
Laith Fuad Abualrob
Mosab Mohammad Jabir
  Supervied by : Eng. Reema Nassar

## Slide 2
Outline
Project management system.
Methodology.
Quantity Survey.
Project Introduction.
Rivet 3D modeling.
Time And Cost Management.
Cost And Price Estimate.
Results And Conclusions.
References.

## Slide 3: Project management system.

## Slide 4: Methodology
Work break down structure.
Quantity Survey Using Rivet Software.
Time schedule using primavera software.

## Slide 5: Quantity Survey.
To assist the client to have an accurate estimate of the volume of work as well as the required budget.
To assist in the accurate preparation of tenders, by providing uniform measurement of quantities.
To give insight into the required variation work amount.

## Slide 6: Quantity Survey.
Data required for the preparation of an estimate or survey .
Drawings.
Specifications.
Rates.

## Slide 7: Delivery Systems
Traditional (Design-Bid-Build)
Design-Build (Turnkey)
Self-performance
Professional Construction Management
Operate Transfer (BOT)

## Slide 8: Traditional (Design-Bid-Build)

## Slide 9: Design-Build (Turnkey)

## Slide 10: Self-Performance

## Slide 11: Construction Contract
Stipulated sum contracts or single fixed cost (Lump sum contracts).
Negotiated Cost plus fee contracts (Cost reimbursement contracts).
Unit price contract (Admeasurements contracts).
Guaranteed maximum price (GMP).

## Slide 13: Project Introduction.
Ramallah
10 Floors
18058 m²

## Slide 14: Project Description

## Slide 15: Rivet 3D modeling.

## Slide 16: structural Rivet 3D modeling

## Slide 17: Floor Definition

## Slide 18: Definition for the Structural Elements

## Slide 19: Beam Section Definition

## Slide 20: Columns Rebar

## Slide 21: Rebar Extension for Shear Walls

## Slide 22: Bars Distribution for Ribs

## Slide 23: Bars Distribution for Ribs

## Slide 24: Architectural Rivet 3D modeling

## Slide 26: Stone Wall Definition

## Slide 27: Door and Windows Definition

## Slide 29: Tile Definition

## Slide 30: Wall Definition

## Slide 31: Time And Cost Management

## Slide 32: Estimating
Work Breakdown Structure (WBS)
Work Breakdown Structure is one form of project management forms; it is the basis for time estimation, resource allocation, cost estimation and collection. Company’s owners and project managers used to breakdown the large projects into smaller manageable projects that can be effectively estimated and supervised. However, the work breakdown structure is often misunderstood and not used as it should be in project management.

## Slide 33
WBS depend on several factors, some of them are:
Size and complexity of the work.
Project manager judgment of work.
Time available to complete the project.
Degree of uncertainty and risk involved.

## Slide 35: Bill of Quantities
Bill of Quantities is (sometimes referred to as a 'BoQ' or 'BQ') is a document, typically prepared by a cost consultant (often a quantity surveyor) that provides measured quantities of the items of work identified by the drawings and specifications in the tender documentation for a project. It is issued to tenderers for them to prepare a price for carrying out the works.

## Slide 36: Project Life Cycle
The major phases in the project cycle that are common to most design and construction projects are:
 Project Planning
 Design
 Construction
 Occupancy

## Slide 37: Project Definition
The parameters needed to define the project in Primavera software:
Project ID: M.O.P.W.H
Project Name: Ministry of Public Works and Housing.
Project Planned Start Date: 1/1/2015
Major Rate Type: Price/Unit.

## Slide 40: Calendar Definition
The parameters needed to define the calendar in Primavera software:
- Work Hours per Day: 8.0 hr/d.
- Calendar Weekly Hours: 8.0 hours for all week’s days but Friday is holiday.
- Hours per Time – Period:
8.0 hr/day.
48.0 hr/ week.
206.0 hr/month.
2496 hr/year.

## Slide 42: Activity Relationship

## Slide 45: Activities Relationships Assignment
According to sequence of activities, take one activity as an example, the following figure shows the relationships assignment between activates:

## Slide 46
Resources Definition

## Slide 47
Resources Definition For Activities

## Slide 48
Resources Definition For Activities

## Slide 49: Results from Primavera
Early start, early finish, late start, late finish, total float and free float for each activity found in the attached report and critical activity.

## Slide 50
budgeted labor cost and budgeted Non-labor cost and Original Duration found in the attached reports.
Results from Primavera

## Slide 51
Results from Primavera
Gantt chart found in the attached Gantt chart sheets.

## Slide 52: Resources Definition

## Slide 53: Cost And Price Estimate.
  Assumption for pricing :
Job overhead cost = 10%
Operating overhead cost = 5%
Profit = 15%
Waste factor for materials = 5%
Waste of mortar in plastering = 13

## Slide 56: Results And Conclusions
As we said in the introduction of this chapter, we applied the principles of project management to analyze our project and we show what an expected life of project management is, so we gain from this project a lot of experience and information in how to deal with projects and manage it in time, cost & performance.
First, we use Revit program to analyze the quantities then make the WBS and activity list and enter it into Primavera Project Planner (16.1) and run the program and take the results.
The total project cost is 9241457 NIS.
The total project price is 12274965 NIS.

## Slide 57: References
Ahmad, H. (n.d.). Quantity Surveying Class Notes.
Ashworth, Alan; Perera, S. (2015). Cost Studies of Buildings Allan Ashworth.pdf, 570.
Course, P. (2012). Construction Cost Estimates, 276.
Dagostino, F. R., & Peterson, S. J. (2011). Estimating in building construction.
Date, B. S., Costs, B., & Arrangements, S. C. (2010). Construction Contracts.
E, R. (2007). Work breakdown structure. Project Management Practices (Work Breakdown Structure), (June), 1–3. https://doi.org/10.1007/0-306-48489-7_4.
Heldman, P. M. P. K. (2005). Project Management JumpStart. Management. Retrieved from http://www.amazon.com/dp/0782136001.
Introduction to Primavera. (n.d.).

## Slide 58
Jackson, B. J., Best, T., & Step, F. (2010). Construction Management.
Juliana, C. N., Ramirez, A. M., & Larkin, B. J. (2005). Construction Management / Design-Build Prepared and Presented by : Construction Management / Design Build, 213. Retrieved from https://www.hillintl.com/PDFs/Construction Management Design Build -11-24-04 Ramirez, Alann.pdf.
Office, P. S., & Division, P. M. (n.d.). Project Management.
PMI. (2013). A Guide to the Project Management Body of Knowledge. Project Management Institute (Vol. 5). https://doi.org/10.1002/pmj.20125.
Portny, S. (2010). Project Management For Dummies 3rd Edition V413HAV.pdf. Retrieved from www.wiley.com.
Richman, L. (2011). Successful Project Management.