## Slide 1: Delay In Construction Project In West Bank
Prepared By:
Mohammad Jaroshi
Murad Abdo
Tariq Iraqi
Supervised by:
Mr. Mohammad Abu Neamah

## Slide 2: Outline:
Background.
Research objective & methods.
Important factors that cause time and cost overrun.
Discussions on effects of delay on participants of project.
Conclusion.
Recommendations.

## Slide 3: Background
Most problem in construction is delay.
Construction contract = contract duration ( specified period of time) = contractor must comply to achieve substantial completion within this time.
For unexpected reasons contractor fails to complete the project within the contract period.
Owner will claim liquidated damages and obtain contractual release extension of time.
Delay analysis based on responsibilities : delay excusable (compensable & non compensable ) and inexcusable
Project delay result from computing activity delay.
Traditional delay analysis method based always on CPM analysis on other words any delay on critical path delay the project completion.

## Slide 4: The Objectives
The objective of this research are:
Determining the level and causes of delays in construction projects.
Explore the relationship between the delayed projects and participants of implementing the project.
Study the effect of delay on the projects in general and effect in contractor and owner.
Determine the relationship between the project delay and its type and size.
Search for solution and how to minimize the causes of delay.

## Slide 5
Topic Selection
Establish Objective
Define the problem
Project Proposal
Develop Research Plan
Literature Review
Field Surveying
Questionnaire Design
Conducting Survey
Result and Data Analysis
Conclusion and Recommendation
Piloting (expert was invited)
The Methodology

## Slide 6: The questionnaire consists of four parts :
General information about the respondent .
Factors that affect the increase in the duration of the engineering projects.
Factors that affect the increase in the cost of engineering projects.
The effects of the delay on the project as a whole and on the participants of the project .

## Slide 7: Data Analysis Questionnaire survey
City name | Questionnaire were sent | Questionnaire were responded
Nablus | 30 | 25
Tulkarem | 21 | 15
Ramallah | 20 | 17
Chart: 
| Nablus | Tulkarem | Ramallah
Questionnaire were responded | 25 | 15 | 17

## Slide 8: Data analysis The most important factors that cause time overrun from Contractor point view
Owner delay in freeing the contractor financial payments.
Slow permits by Government agencies .
Poor site conditions(location, ground).
Poor economic conditions (currency, inflation rate).
Unrealistic contract durations imposed by owner.

## Slide 9: Data analysis The most important factors that cause time overrun from Owner point view
Major disputes and negotiations.
Insufficient number of staffs (contractor).
Poor site conditions(location, ground).
Slow information flow between project team members.
Spend some time to find sub-contractors company.

## Slide 10: Data analysis The most important factors that cause time overrun from Consultant point view
Owner delay in freeing the contractor financial payments.
Poor site management.
Back of follow up for the project schedule and absence of continuous tracking.
Insufficient number of staffs (contractor).
Inadequate contractor experience.

## Slide 11: Data analysis The most important factors that cause time overrun from All respondents point view
Owner delay in freeing the contractor financial payments
Poor site management
Strikes, occupation attacks and borders closures
Major disputes and negotiations
Insufficient number of staffs (contractor)
Poor economic conditions (currency, inflation rate)
Back of follow up for the project schedule and absence of continuous tracking
Delay of material delivery to site
Suspension of work by owner or contractor
Inadequate contractor experience

## Slide 12: Data analysis The most important factors that cause cost overrun from All respondents point view
Inability of the contractor to be adopted properly with the project environmental.
Low communication of donors to compensate any bad result that may come from the economic political situation.
Influenced by the total cost of the project due to delays.
Fluctuations in the cost of building materials.
Lack of cost planning /monitoring during pre-and post contract stages.

## Slide 13: Data analysis Additional cost of delayed project
Chart: 
| Increase | Decrease | Remain as it is
75.4% 5.3% 19.3% | 0.75439 | 0.052632 | 0.19298
75.4% 5.3% 19.3% | 0.75439 | 0.052632 | 0.19298

## Slide 14: Data analysis The percentage of increasing cost of delayed project
Chart: 
| 10%-20% | 20%-30% | 30%-50% | more than 50%
 | 31 | 11 | 1 | 0
 | 0.72093 | 0.25581 | 0.023256 | 0

## Slide 15: Data analysis Productivity rate of labors when the project delay
Chart: 
| Incease | Decrease | Remain as it is
 | 14 | 25 | 18
 | 0.24561 | 0.4386 | 0.31579

## Slide 16: Data analysis Quality of work in delayed project
Chart: 
| Increase | Decrease | Remain as it is
 | 0.10526 | 0.49123 | 0.40351

## Slide 17: Data analysis The additional costs of the contract value paid by the Contractor as a percentage of delayed projects
Chart: 
| (1%-5%) of contact cost | (6%-10%) of contact cost | (11%-15%) of contact cost
 | 0.45614 | 0.47368 | 0.070175

## Slide 18: Conclusions
The time overrun cause almost from owner and contractor in addition to the external factors because :
Owner delay in freeing the contractor financial payments is related to owner.
Insufficient number of staffs (contractor) is related to contractor.
Strikes, occupations attacks and borders closures is related to external factors.
The cost overrun is a normal result of the delay .
The cost of the project will be increased if the project is delayed .
The quality of the project will be reduced in delayed project.
productivity of the workers will be reduced due to delay of current project.

## Slide 19: Recommendation
Owner should pay progress payment to the contractor on time .
The owner must take enough time to think about the shape and design of the construction.
Owners are recommended to have technical staff who is able to manage the different stages.
Contractors are recommended to be aware on the construction materials.
Contractors are advised to establish stores construction materials required.
Contractors are recommended to qualified and quantified technical staff with the appropriate experience.
Contractors are recommended to prepare the way for the statement and the schedule for the project.
Designer are recommended to develop the way of showing the Architectural Design from two dimension to three dimension.

## Slide 20: Presentation date: 19/12/2013.