## Slide 1
An-Najah National University
Engineering Faculty
Civil Engineering Department
Construction project management
Submitted in partial fulfillment of construction project management for the bachelor degree in civil engineering
Prepared by:
Omar Dao’ur Abed-Allah Sawalmeh
Mohammad Fu’ad Mohannad Abu Semri
Submitted to:
Dr. Barraq Joma’a
2011

## Slide 2
The project consists of two parts
Part one : Project Management Principles
Part two: The Applied Project

## Slide 3: Part one
Project Management Principles

## Slide 4: The definition of (project)?
A project is a temporary endeavor undertaken to accomplish a unique product or service with a defined start and end point and specific objectives that, when attained, signify completion.
PMBOK

## Slide 5: What do we mean by (Project Management)?
Project management is the discipline of planning, organizing, securing and managing resources to bring about the successful completion of specific project goals and objectives. It is sometimes conflated with program management, however technically that is actually a higher level construction: a group of related and somehow interdependent engineering projects.
Project management is the application of knowledge, skills, tools, and techniques to project activities in order to meet or exceed stakeholder needs and expectations from a project.

## Slide 6
Project management is the science (and art) of organizing the components of a project, whether the project is development of a new product, the launch of a new service, a marketing campaign, or a wedding. A project isn't something that's part of normal business operations. It's typically created once, it's temporary, and it's specific. As one expert notes, "It has a beginning and an end." A project consumes resources (whether people, cash, materials, or time), and it has funding limits.

## Slide 7: Project Management basics
Definition
Planning
Execution
Control
Closure

## Slide 9: The triple constraint

## Slide 10: Part Two The Applied Project

## Slide 11: Description of the project
The project is a school building
Sites in Sulfeet – West Bank
The owner is the ministry of education – Palestinian Authority
The building consists of three stories
The area of the school is 671m2

## Slide 12: Sequence of works
The main steps we have followed in our project is:
  Work Breakdown Structure (WBS).
  Quantity surveying.
  Bill of quantity (BOQ) preparation; quantities, cost, resources, and man hours.
  Activities durations.
  Project cost.
  Project duration.

## Slide 13: WBS
Work breakdown structure is a tool used to define and group a project's discrete work elements in a way that helps organize and define the total work scope of the project.

## Slide 14: WBS of the project

## Slide 15: Quantity surveying
We have used M.Excel to find the quantities of each activity due to the WBS, the calculations include (steel, concrete, frame work,..etc).
We have used the symmetry (if there), to facilitate the calculations.
  For example there are five different volumes of footings, we have calculated for one footing of each type then multiple with its number.

## Slide 16: Sample calculation
Calculations of concrete volumes and frame work areas:

## Slide 17: (Cont’d)
Calculations of steel weighs:

## Slide 18
Duration =( Mhr*total quantity) /n. of labors * no of hours
In this project : the labor work in crew such as civil crew included 5 workers and work 8 hours in day
Example :
The steel for the first slab = 5.7 ton and Mhr for steel in slab = 25
Duration =( 5.7 * 25 ) /(5*8) = 3.56 days
This means you need one crew to finish steel work in slab in 4 days
Activities durations :

## Slide 19: Project Budgeting
Estimation cost of the material , labor and non labor, for each activity , it was collect tha data from contractors .
And here some excel calculation

## Slide 20: Calculate the cost of resources (Labor/Material/ equipment)
labor

## Slide 22
Resources and cost

## Slide 23: Primavera analysis
The primavera used to :
Scheduling
Project network
Project budgeting
Project duration and CBM analysis
Resources leveling

## Slide 24
Result from excel
Result from primavera
768900.8
768900.64
The result excel and primavera are the same

## Slide 27: conclusion
The quantity surveying for each activity most be calculated according to work breakdown structur,and then the cost for activity must be determined to calculate total cost and total duration on the project.
The management principle must be used to determine the early start, early finish, free float, total float for each activity.

## Slide 28: Cont’d
The scheduled project duration is 187 work days
38 % of activities are critical .
The price per meter square as total is approximately 1383.1 NIS
The project indirect cost estimated to be 10 % of cost .
The profit of the project is 10 % of the total cost ( direct & indirect )

## Slide 31
Thank you for
your attention