## Slide 1: The factors leading to speed up the construction projects
Beesan Asous – Reg. No: 11243618
Farah Eid – Reg. No: 11214143
Under supervision of: Dr. Hussein Abu-Zant

## Slide 2: Abstract
We will study it in an equivalent way by studying the factors that help speed up the construction projects (They are two sides of one coin).
The aim of this research is to know these factors. A questionnaire was written to study. It consists of two parts:
Part I: Company general information.
Part II: The factors that speed up construction projects.
The questionnaire will be given to the contractors, owners and supervisors then will be analyzed.

## Slide 3: Introduction
The main causes of delays are:
Economic problems, like delayed payment.
Materials procurement.
Changes in drawings.
Contract modification.
Staffing problems.
Poor supervision.
Construction mistakes.
Equipment unavailability.
Design errors.
Complexity of the project.
Lack of contractors and designers experience.
Changes the projects scope.
External effects.

## Slide 4: What is delay?
Project delay is the default to deliver the project to owner due to a time difference between the actual time of the project and the planned time. Where the scheduling of work planning is used.

## Slide 5: Types of delay
Delays
Critical or non-critical
Excusable or non-excusable
Compensable or non-compensable
Concurrent and non concurrent

## Slide 6: objectives
Identify the main reasons for delays by the owner, contractor and designer.
Getting recommendations to assist those responsible parties of the delay to avoid it.

## Slide 7: Significance of work
Try to reduce the delays that lead to a difference between the actual time and the planned time and thus reduce the effects resulting from the delay.
Trying to limit the effect of the delay in case the situation comes out of control.
Give recommendation to avoid delays as much as possible.

## Slide 8: Factors leading to speed up the construction projects
From the owner's point of view:
Simplicity and clarity of owner requirement by the owner.
Payment on scheduled time by the owner.
Avoiding scope changes by the owner.
Quick responses from the owner.

## Slide 9
From the contractor's point of view:
Adequate experience staff and manpower efficiency within the project management team.
Proper utilize tools to manage the project by the project management team organization.
Adequate leadership on part of the project manager.
Creativity of decisions in case of occurrence of delays by project management team.
Unity between participants in case there are large number of participants within the project.
Proper project schedule by the project management team.
Appropriate construction methods by the contractor.

## Slide 10
From the designer's point of view:
Availability of clear and complete drawings by the designer.
Practical design by the designer.
Efficiency of supervision by the designer.

## Slide 11
Other:
Consultation with the owner by the project management team organization.
Reasonable risk allocation by the project management team leads to avoid time and cost delays.

## Slide 12: study procedure
The Procedures were:
Contracting company visit.
Interview with the supervisor.
Attaining BOQ of the project.
Scheduling of the project using MS Project.
Determine the existing delay.
Distribute the questionnaire.
Analyze questionnaire using SPSS.

## Slide 13: Data collection
Questionnaires, as know, contain a series of questions related to the research being conducted.
BOQ, as known, an itemized list of resources related to activities.
Interview, as known, a conversation directed by the researcher on the one hand and a person or other persons on the other to collect the necessary information.

## Slide 14: Results and recommendations
The results of the interview:.
Lack of helpers.
Bad management.
Political conditions.
Weather conditions.
The high prices of materials and the change in the price of the currency compared to the prices subject to tender and the main reason of the competition between the contractors which led to the slash prices.

## Slide 15
The results of the Questionnaire:
The percentage of all the factors established exceeded 70%, but the most dominant reason was:
Qualified labor and adequate experience from the project management team in the rate 91.4%.
When applying any construction project we recommend choosing a teamwork with experience, qualified labor and commitment.