## Slide 1: Financial Risk Management Affecting Building Projects in WB, Contractor’s Perspective
Prepared by:
Alaa Al-Araj
Ahmad Freehat
Hazza’a Ammori
Supervised by:
Eng. Reema Bdair

## Slide 2: Research Methodology
Problem definition, Research aim and Research objectives
Theoretical Background & Literature Review
Determination of R-Strategy
Questionnaire building and sample size determination.
Questionnaire analysis
Recommendations.

## Slide 3: Methodology – Research Strategy
Research strategies are usually divided into two main types:
1- Quantitative research
2- Qualitative research
This research mixes both of them but depends mainly on conducting questionnaire survey.

## Slide 4: Questionnaire Final Form
It consists of two parts :
The first one asks about general questions related to the company and the questionnaire filler.
( 6 Questions )
The second one measures the degree of severity and controllability of 24 widespread and well-known financial risk factors.

## Slide 5: Questionnaire Analysis
Chart: Who filled out this form (his\her Career)?
| manager of the company | Sub-manager | Accountant | Engineer | Other
 | 5 | 1 | 0 | 5 | 1

## Slide 6: Questionnaire Analysis
Chart: Who is responsible for estimating financial risks that affect construction projects in your company?
| manager of the company | Sub-manager | Accountant | Engineer | Other
 | 11 | 0 | 0 | 0 | 1

## Slide 7: Questionnaire Analysis
Chart: How many experience years does your company have in construction sector?
| less than 5 years | (5-10) years | (10-15) year | (15-20) year | other( ..................)
 | 0 | 4 | 4 | 2 | 2

## Slide 8: Questionnaire Analysis
Chart: What is the system adopted by the company in the financial risk assessment, its impact and the ways to minimize them?
| Computerized programs | Expertise and experience | A mixture of the two sides | other (..............)
 | 0 | 2 | 10 | 0

## Slide 9: Questionnaire Analysis
Chart: How many full time employees does your company have?
| less than 10 | (10- 20) | (21-30) | (31-40) | other(............)
 | 4 | 2 | 4 | 2 | 0

## Slide 10: Questionnaire Analysis
Chart: In general and from your own perspective, is your company able to predict the probable financial risks?
| Always | Often | Sometimes | Never
 | 5 | 6 | 1 | 0

## Slide 11: Questionnaire Analysis
The severest ten main factors in term of the degree of severity were:
Bankruptcy of the owner or financier.
Delays in payments:
Contractor's debts before the start of the project (Existing debt).
Monopolization of materials and equipment as a result of Israeli closures and unforeseen political conditions.
Foreign currency fluctuation and Exchange rate fluctuation.
Error in the previous estimate for the project and its related costs account (Unsound pre-estimation of the project cost.)
Inflation
Labor strikes
Contractor's bankruptcy
Inadequate terms and conditions in tender documents.

## Slide 12: Questionnaire Analysis
The top ten factors in terms of the degree of being out of control where:
Monopolizing of materials due to closure and other unexpected political conditions.
Bankruptcy of the funder or the owner
Take-up of shares
Financial failure of the contractor (insufficient funding/ Contractor’s bankruptcy)
Foreign currency fluctuation and Exchange rate fluctuation
Inflation
Source of loan
delay in payments
labor strikes
Delay in the first payment.

## Slide 13
 | Risky Factor | Severity | Controllability
1 | Delay in Payments | Very Severe | Moderate
2 | Delay in the first payment specially | Moderate | controllable
3 | Foreign currency fluctuation and Exchange rate fluctuation | severe | Moderate
4 | Inflation | severe | Moderate
5 | Inadequate terms and conditions in tender documents. | severe | controllable
6 | Having to break up partnerships between companies, in a project or both | Moderate | controllable
7 | Labor strikes | severe | controllable
8 | Unsound pre-estimation of the project cost. | severe | controllable
9 | Financial failure of the contractor (insufficient funding/ Contractor’s bankruptcy) | severe | Moderate
10 | Bankruptcy of the funder or the owner | Very severe | Moderate
11 | Lack of financial liquidity management during the project | severe | controllable
12 | Monopolizing of materials due to closure and other unexpected political conditions. | Very severe | Moderate
13 | Fraud | severe | controllable
14 | Performance bond requirements | Moderate | controllable
15 | Interest Type (Fixed, Floating, or capped) | Moderate | controllable
16 | Changes in interest rate | Moderate | controllable
17 | Availability of loan | Moderate | controllable
18 | Loan period | Moderate | controllable
19 | Source of loan | Moderate | Moderate
20 | Existing debt | Very severe | controllable
21 | Insurance | Moderate | controllable
22 | Taxes | severe | controllable
23 | Time and amounts of dividend payments | Moderate | controllable
24 | Take-up of shares | Mild | Moderate

## Slide 14: Recommendations
1- Bankruptcy of the financier or the owner:
If the contractor feels that the case here will occur, he shall try to get a bank guarantee which ensures that the owner or the funder has the ability to pay.
Avoiding taking projects which are funded by the Palestinian financial ministry.

## Slide 15
2- Delay in payments
(1) Asking for advanced or mobilization payment
(2) Loading of rates
(3) Adjustment of work schedule to late start timing..
(4) Reduction of delays in receiving revenues.
(5) Achievement of maximum production in the field to increase the monthly payments.
(6) Reducing the retention.
(7) Adjust the timing of delivery of large material orders to be with the submittal of the monthly invoice.
(8) Delay in paying labor wages, equipment rentals, material suppliers and subcontractors.
(9) Billing ahead of schedule.

## Slide 16
3- Owed debts on the contractor before starting the project :
Asking for sufficient advanced payment or mobilization payment.
Loading of rates by increasing the prices of the earlier items which guarantee more income at the early stages and help in debts repayment.
Delay in some duties as much as possible such as: labor wages, material suppliers, equipment rentals and/or subcontractors.
4- Israeli Closure of the West Bank
Seeking for local alternatives and alternative materials.
Prolonging the duration of the project as a safety margin.
Increasing the value of the bid (the price).
Risk allocation (sharing risk between the key parties).
Avoiding far projects or projects at risky areas.

## Slide 17
5- Foreign currency fluctuation and Exchange rate fluctuation
This is one of the most frequent problems in Palestine since projects aren’t usually locally funded. This problem can be solved or avoided by inserting clear statements in the contract which fix and set the exchange rate.

## Slide 18
6- Unsound pre-estimation of the project cost (faulty estimation)
To avoid this, estimations and calculations should be done by specialized ones in the company.
Taking into account both of the history of material prices fluctuation and future expectations (during the life of the project).
Using of modern technologies and methods as much as possible in finding out quantities and cost estimation.
An in-depth study of the contract is needed to avoid any ambiguity which may lead to wrong evaluation and estimation.

## Slide 19
7- Inflation:
If the life time of the project is too long, the contractor can increase the price to avoid the case of inflation.
If the preceding choice leads to unsound value and his financial ability is unstable, then the contractor may avoid this kind of projects.
If possible, linking the value of the project in the contract with a fixed-kind value.

## Slide 20
8- Labor strikes
9- Financial failure of the contractor (insufficient funding):
Crew of qualified assistants should be employed or experts should be consulted on and on.
Avoiding projects which are over the financial ability of the contractor.
Establishing partnerships with other companies (if preliminaries for this risk appear) to assure financial liquidity.
Delivery of the project to other able subcontractors.
10- Inadequate terms and conditions in tender documents

## Slide 21
Thank You