## Slide 1
Time and Cost Estimation of (Ali Nayfeh School)
Prepared by :
Husam Jehad Yousef .
Adnan Karim Amira .
Mohammed Basem Mahamdeh .
Murad Azzam Odeh .
Moaz Raed Nuirat .
Under supervision of: Dr. Reema Nassar.

## Slide 2
Outline
Introduction.
Methodology.
Revit.
Primavera.
Bill of Quantity (BOQ).
01
02
03
04
06
07
08
Case Study.
Final Results.
05
Lumion.

## Slide 3
Introduction
  Study objective.
Significant of Study.
What is a Project ?
01
02
03

## Slide 4
What is a Project ?
A project is a temporary endeavor undertaken to produce a unique product or service.
TEMPORARY
UNIQUE
Beginning
And End
New
Unfamiliar

## Slide 5
Make a quantity survey and cost estimate for all project items.
Make scheduling for all activities in the project and determine the appropriate time.
Show the building details by build 3D model presentation by using software programs.
The importance of the project is the application of various management aspects such as managing time, costs, resources, quality control, and facilitating the relationship between project members, as the application of these aspects and their introduction into projects affects the way the project is conducted and better managed by using different engineering programs that greatly help in this aspects.
Significant of study
Study objective

## Slide 6
Case Study
Location: In the North Part Of Tulkarm City.
Land Area: About 5000 Square Meters.
Construction Area: Three Floors and a Basement of about 3571 Square Meters.

## Slide 7
Methodology
Data collection.
Quantity Survey Using Revit Software.
Bill Of Quantity.
3D Modeling Using Lumion.
Time schedule using Primavera.

## Slide 8
Definition: A BIM software used to design a building or a structure and its components in 3D.
Benefits:
1.Project Preview.
2.Simple and more accurate
quantity estimation.
3.Quick design changes
4.Rendering Presentation.

## Slide 9
How We Used Revit Software In Our Project ?
Customize 2D AutoCAD Plans.
Draw Levels.
Insert 2D AutoCAD on levels.
Draw 3D Model for the Entire Project.
Draw Sections and Facades.
Extract Architectural & Structural Quantities.

## Slide 10
2D AutoCAD Plans

## Slide 11
Levels

## Slide 12
Architectural Model During Building

## Slide 13
Final Architectural Model

## Slide 14
Storey | Stone (m2) | Plaster (m2) | Paint (m2) | Block (m2) | Mortar (m2) | Tiles (m2)
Base. | 93 | 563 | 563 | 317 | 386 | 386
GF | 557 | 2858 | 2585 | 4646 | 1109 | 1109
FF | 555 | 2147 | 2147 | 1276 | 981 | 981
SF | 555 | 2147 | 2147 | 1276 | 981 | 981
Roof | 100 | 106 | 106 | - | - | -
Total | 1860 | 7821 | 7548 | 7515 | 3457 | 3457
Architectural Quantity:

## Slide 15
Structural model

## Slide 16
Structural model

## Slide 17
Foundation No | Number of foundations | Concrete (m3) | Steel (tons)
F1 | 33 | 66 | 17.7
F2 | 29 | 73.37 | 
F3 | 4 | 18.82 | 
F4 | 2 | 0.6 | 
F5 | 2 | 1 | 
Shear wall | 9 | 12.98 | 
Retaining wall | 2 | 28.49 | 4.2
Column neck | 70 | 12.79 | 3.07
 | Total | 213.75 | 24.97
Blinding concrete B150 (m3) | 51.72
Structural Quantity:

## Slide 18
Tie beam No. | Concrete (m3) | Steel (tons)
T. B. 1 | 15.14 | 2.62
T. B. 2 | 5.50 | 
T. B. 3 | 0.24 | 
T. B. 4 | 5.64 | 4.4
T.B.5 | 13.0 | 
T.B.6 | 29.58 | 
T.B.7 | 2.78 | 
T.B.8 | 1.3 | 
T.B.9 | 1.28 | 
FLOOR | 85 | 7.3
Total | 159.46 | 14.32
Structural Quantity:

## Slide 19
Element name | Number | Concrete (m3) | Steel (tons)
C1 | 240 | 120.69 | 24.25
C2 | 19 | 4.81 | 
C3 | 6 | 4.38 | 
C4 | 6 | 7.08 | 
Shear walls | 39 | 183.31 | 31.3
Retaining walls | 2 | 40.4 | 4.2
 | Total | 360.67 | 59.75
Structural Quantity:

## Slide 20
Element name | Concrete (m3) | Steel (tons)
Beams | 387.3 | 84.9
Ribs | 85.38 | 
6cm slab | 133.64 | 17.7
Total | 606.32 | 102.6
Element name | Concrete (m3) | Steel (tons)
Stair | 43.04 | 4.6
Structural Quantity:

## Slide 21
Insulation | Area (m2)
For footing | 296.58
For column neck | 155.72
tie beams | 890.51
Total | 1342.81
Structural Quantity:

## Slide 22
Sample of Hand Calculations

## Slide 23
Sample of Hand Calculations

## Slide 24
Sample of Hand Calculations

## Slide 25
Lumion Software :
Definition : Visualization Software Made For Architects.
Benefits:
It’s the perfect way to show your clients or other professionals how your idea can work.
Professionals such as constructors and gardeners will understand perfectly what they are going to do in the site.
Perfect Quality In Rendering.

## Slide 26
Lumion Interface :

## Slide 27
Definition: Its a software used to plan and manage all kinds of complex projects while satisfying all requirements.
Benefits:
  Time schedule for the project.
  Efficient progress tracking.
  Analyze alternative plans.
Primavera (P6) Software :

## Slide 28
Project Definition

## Slide 29
Definition:
It is the specific calendar for the project, which contains the number of daily, weekly and monthly working hours, and through which the work hours in the project are determined.
The parameters needed to define the calendar in Primavera software:
Calendar Name.
Work Hours per Day: 8.0 hr/d.
Calendar Weekly Hours: 8.0 hours for all week’s days when Friday is holiday.
Calendar Definition

## Slide 30
Calendar Layout :

## Slide 31
Work BreakDown Structure (WBS)

## Slide 32
Example Of Activities

## Slide 34
Assign Activities Relationships
According to sequence of activities, take one activity as an example, the following figure shows the relationships assignment between activates:

## Slide 35
Results from Primavera
Gantt chart found in the attached Gantt chart sheets.

## Slide 36
1. The working days for the school project was estimated to be (460) days.
2. The calendar days for the school project was estimated to be (537) days.
Results from Primavera

## Slide 37
Cost and Price Estimate

## Slide 38
Cost and Price Estimate
  Assumption for pricing :
Job overhead cost = 10%
Operating overhead cost = 3%
Profit = 5%
We make the BOQ in dollar currency and use local costs of the construction materials in Palestine

## Slide 39
Example On BOQ :

## Slide 40
Example On Calculating The Price:
Total Cost for Ground Foundation (B300) :
Price = Direct Cost + Indirect Cost + Profit.
Direct cost = Unit Cost ( $/m3 ) * Quantity =
( Labor cost + Concrete Cost + Steel Cost + Insulation Cost + Formwork Cost ) * Quantity
= {(15)+(290/3.2)+()102.4 * 3.3) / 3.2)+5+(0.02 *4 *1400 /3.2)}($/m3) * 123.46m3 = 31016.3 $
Indirect Cost = (Job Overhead = 10% + Operating Overhead = 3%)
Job Overhead (10%) = Direct Cost * 1.1 = 31016.3 * 1.1 = 34117.9 $
Operating Overhead (3%) = 34117.9 * 0.03 = 1,023.537 $
Total Cost = 34117.9 + 1,023.537 = 35141.4 $
Price = Total Cost * ( 1 + Profit % ) = 35141.4 * 1.05 = 36898.5 $
Bid Factor = ( Price / Direct Cost ) = 36898.5 / 31016.3 = 1.18965

## Slide 41
Final Result
Activity work | Price ($)
Site Preparation | 5000.00
Foundation Activity | 142302.6847
Shear Wall & SOG | 60998.2725
Basement Floor Activity | 97493.76067
Ground Floor Activity | 335116.4656
First Floor Activity | 305565.0644
Second Floor Activity | 290341.1014
Roof Activity | 43992.23033
Total Price | 1280809.58

## Slide 42
The total price for this school project was estimated to be 1280809.58 $.
Price per meter square = .
Final Result