## Slide 1: Delay in Construction Projects in Palestine From Contractors Perspective
Prepared by:
Mohammed Bassam Omar Zorba
Osama Abu Alrob Omar Najjar
Under supervision of:
Dr. Mohammed Abunemeh

## Slide 2
Outline
Introduction
Statement of Problem
Objectives of the study
Significance of the study
Research methodology
Confirmation of delay hypothesis
Questionnaire content
Sample size
Results
Recommendations

## Slide 3
Introduction
Construction sector is one of the most effective sectors affecting the economy of Palestine due to:
The significant connection with other sectors.
Its great contribution to the Palestinian Gross Domestic Product (GDP).

## Slide 4
Introduction
Construction industry in Palestine suffers from several problems such as :
Israeli occupation
Shortage of skilled labor
Shortage of materials and equipment
Weak planning strategies
TIME OVERRUN

## Slide 5
Statement of Problem
Time is the driving force of project success.
The problem of delays in the construction industry is a global phenomenon and the construction industry in Palestine is no exception.
Delays occur in most construction projects and the magnitude of these delays varies considerably from a project to another.

## Slide 6
Objectives of the Study
The main objectives of this study are:
To identify the major causes of delays of both buildings and highway construction projects in Palestine.
To determine the most important actions that can be taken to minimize delay.

## Slide 7
Significance of the Study
This study discusses the most important causes of delay in construction projects ,
Discusses the most important actions to minimize delay in construction projects and
Ends up with recommendations to minimize or eliminate delay in construction projects in Palestine.

## Slide 8
Research Methodology
Objectives
Literature Review
Questionnaire
Consult Experts
Questionnaire Pilot Test
Interviews
Questionnaire Distribution
Data Collection

## Slide 9
Research Methodology
Results
Actions to reduce delay
Causes of delay
Conclusion and Recommendations
Data Analysis
SPSS
Excel

## Slide 10: Confirmation of Delay Hypothesis
NO. | Project Description | Original Duration | Actual Duration | Deviation | % of Deviation from Plan
1 | Constructing Faculty of Medical Sciences in Arab American University-Jenin | 270 | 297 | 27- | -10
2 | Constructing Taxi’s Parking Lot of Qabatia-Municipality | 90 | 276 | 186- | -206
3 | Constructing Al-Thaghra School in Tubas | 430 | 675 | 245- | -56
4 | Paving the Main Street of Fahma Town | 91 | 66 | 25+ | +27
Sample Projects:
Table ‎1: The actual and planned schedules for some executed construction projects
* (+) means ahead of schedule. * (-) mean behind schedule.

## Slide 11: Confirmation of Delay Hypothesis
The following figure compares between the actual and planned delivery dates of some construction projects executed in Palestine.
Chart: Project Number
Planned Duration | 90 | 302 | 270 | 120 | 430 | 120 | 45 | 120 | 60 | 305 | 518 | 551 | 468 | 430 | 365 | 120 | 150 | 90 | 60 | 91
Actual Duration | 276 | 518 | 297 | 294 | 635 | 207 | 102 | 300 | 550 | 1035 | 1778 | 1104 | 682 | 675 | 365 | 254 | 218 | 85 | 94 | 66
Figure ‎1: The deviation between the actual duration and planned duration

## Slide 12: Confirmation of Delay Hypothesis
Figures 2 shows that about 85% of the previous projects delayed beyond the stipulated date of delivery.
Chart: 
| Delayed | As planned
Delayed As planned | 17 | 3
Figure ‎2: The percent of delay in some executed construction projects

## Slide 13: Questionnaire Content
The questionnaire was divided into three main parts:
Part one: Respondents Characteristics: General information about respondents.
Part two: Causes of delay in construction projects:
Causes of delay in construction projects categorized into five groups according to (Gunduz,2013).
Part three: Actions to reduce the delay in construction projects.
Actions the contractor can take to accelerate the project and reduce the delay.

## Slide 14
The minimum sample size for the questionnaire was calculated using the sample size formula for finite population.
The minimum size was found to be 57.
A sample of 65 questionnaires was used.
Sample Size

## Slide 15
Governorate | Sample size
Nablus | 45
Jenin | 14
Qalqiliah | 6
The sample size for each governorate has calculated using a weighted average. Where the size of each governorate is shown in table 2.
Sample Size
Table ‎2: The sample size for each governorate

## Slide 16: Respondent Characteristics analysis
Variable | Class | Frequency | %
Governorate | Jenin | 12 | 20.3
 | Qalqiliah | 6 | 10.2
 | Nablus | 41 | 69.5
Job title | Project Manager | 29 | 49.2
 | Site Engineer | 22 | 37.3
 | Observer | 4 | 6.8
 | Other | 4 | 6.8
Academic qualification | B. A | 45 | 76.3
 | M.SC. | 5 | 8.5
 | PhD | 2 | 3.4
 | Other | 7 | 11.9
Experience | Less than 5 years | 10 | 16.9
 | 5-10 years | 24 | 40.7
 | 10- 15 years | 7 | 11.9
 | More than 15 | 18 | 30.5
Table 3: Distribution of sample according to Respondent’s Characteristics

## Slide 17: Respondent Characteristics analysis
Classification | Frequency
First stage building A | 16
First stage building B | 9
Second stage buildings | 15
Third stage buildings | 7
Forth stage buildings | 6
Fifth stage buildings | 4
First stage roads | 9
Second stage roads | 7
Classification | Frequency
Third stage roads | 9
Forth stage roads | 3
Fifth stage roads | 12
First stage water and sewerage | 4
Second stage water and sewerage | 6
Third stage water and sewerage | 4
Forth stage water and sewerage | 6
Fifth stage water and sewerage | 6
Table 4: Classification of the respondents

## Slide 18: Relative Importance Index (RII)
useful technique used to establish the relative importance of various items identified as responsible for some problem.
RII = | 
RII = | 
Where:
RII: relative importance index
Pi: respondent’s rating of the item
Ui: number of respondents placing an identical rating on the item
N: sample size

## Slide 19: Results
Rank | Causes of delay | Categories | RII
1 | Delay in payments for completed work by owner | Financial | 4.71
2 | Shortage of skilled labors | Labor | 4.52
3 | Ineffective planning and scheduling of project by the contractor | Managerial | 4.42
4 | Difficulties in funding project by contractor due to lack of cash | Financial | 4.4
5 | Poor site management and supervision by the contractor | Managerial | 4.35
6 | Inadequate experience of site engineer | Managerial | 4.3
7 | Owner’s change orders during construction | Managerial | 4.27
8 | Insufficient data collection and reconnaissance before bidding by the contractor | Managerial | 4.2
9 | Low productivity of labors | Labor | 4.13
10 | Inability of contactor to manage his projects due to their large number and complexity | Managerial | 4.08
Table ‎5: The most important ten causes of delay with regardless to their category

## Slide 20: Results
Managerial related causes |  | 
Rank | Causes of delay | RII
1 | Ineffective planning and scheduling of project by the contractor | 4.42
2 | Poor site management and supervision by the contractor | 4.35
3 | Inadequate experience of site engineer | 4.3
Table ‎6: The most important three related managerial causes of delay

## Slide 21: Results
Financial related causes |  | 
Rank | Causes of delay | RII
1 | Delay in payments for completed work by owner | 4.71
2 | Difficulties in funding project by contractor due to lack of cash | 4.4
3 | Depending on loans from banks and paying high interests | 3.72
Table 7: The most important three related financial causes of delay

## Slide 22: Results
Construction material related causes |  | 
Rank | Causes of delay | RII
1 | Shortage of construction materials in market | 3.74
2 | Unreliable suppliers | 3.66
3 | Delay in material delivery | 3.64
Table 8:The most important three related construction material causes of delay

## Slide 23: Results
Labor related causes |  | 
Rank | Causes of delay | RII
1 | Shortage of skilled labors | 4.52
2 | Low productivity of labors | 4.13
3 | Lack of experience of labors | 4.08
Table 9: The most important three related labor causes of delay

## Slide 24: Results
Table ‎10: The most important three related external causes of delay
External delay causes |  | 
Rank | Causes of delay | RII
1 | Delay in obtaining permits from municipalities and ministries | 3.81
2 | Equipment malfunction | 3.66
3 | Delay in providing services from municipalities | 3.64

## Slide 25: Results
Table ‎11: Ranking of the group causes
Rank | Group | RII
1 | Managerial related causes | 3.91
2 | Financial related causes | 3.90
3 | Labor related causes | 3.82
4 | Construction material related causes | 3.35
5 | External related cause | 3.28

## Slide 26: Results
Rank | Actions | RII
1. | Using cash payment to get requirements faster | 4.47
2. | Increasing number of labors | 4.17
3. | Working on more than one activity at the same time | 4.12
Table ‎12: The most important three actions

## Slide 27: Recommendations
Recommendations to Contractor:
Use the most sophisticated software that is available for planning and scheduling
Maintain a continuous site supervision and keep updating the schedule regularly.
Maintain a regular periodical maintenance for his equipment.
Motivate and train the unskilled labors to achieve the desired skills and achieve the maximum possible productivity.

## Slide 28
Recommendations to Owner:
Pay the contractor for the completed works on the date agreed upon in the contract to avoid the negative cash flow that would result to the contractor.
Avoid the slowness of decision making.
Recommendations

## Slide 29
Recommendations to Consultant:
Not to delay the inspection process in order to give the approval for completed works.
The owner, consultant, and contractor are recommended to improve the communication and coordination between each other.
Recommendations