## Slide 1: CONSTRUCTION PROJECT MANAGEMENT REALITY IN PALESTINE: MES CASE STUDY
FaKHRI ANAN JAYYOSI
JAWDAT AYMAN RABBa’
MAHER MOHAMMAD BARAKAT
MUAIAD KHALED ABDUL-DAYEM
Supervisor: Dr. Mohhamed aBU NI’MEH

## Slide 2: GRADUATION PROJECT 1 SUMMARY
Construction sector participates with 14% and 23% in the national income in the West bank and Gaza respectively.
Problem statement:
Lack of appreciation towards adopting creative management methods
Big misunderstanding towards management concepts and its benefits
Negligence towards BIM concept.

## Slide 3
Case study information.
Location: in the north western part of Nablus city
Land area: about 4800 square meters
Construction area: three stories of about 5700 square meters.

## Slide 4
Methodology:

## Slide 5: LIMITATIONS
The plans that were acquired were preliminary design plans.
This graduation project process was only applied to structural and architectural plans.
Overhead and profit percentages were stated as a lump percentage of 20%.
Tank walls and isolation (16,000 NIS), and interior stadium works (35,290 NIS) were not compared.

## Slide 6: REVIT
Definition: A BIM based software to create a model consisting of smart information.
Benefits:
Simpler and more accurate quantity estimation.
Reduce repetition.

## Slide 7
Defined data and inputs:
2D plans as AutoCAD files.

## Slide 8
Levels

## Slide 9
Zones.
ZONE 1 ZONE 2 ZONE 3
AREA = 1970 m2 AREA = 1737 m2 AREA = 863 m2

## Slide 10
Elements Definition and modelling.
Structural:

## Slide 12
Architectural:

## Slide 13
Quantity survey.
Structural:
Sub structure | Steel (ton) | Concrete(m3)
Footings | 154.2 | 825.4
Tie beams | 13 | 86.1
Total | 167.2 | 911.5
Super Structure |  | Steel (ton) | Concrete(m3)
B2 | Slabs | 29.7 | 271.6
 | Columns | 29 | 138.4
B1 | Slabs | 44 | 222.56
 | Columns | 13.8 | 88.85
GF | Slabs | 50.31 | 345
 | Columns | 21.22 | 148.2
Roof | Slabs | 45.4 | 300.5
 | Columns | 1.37 | 7.56
Total |  | 234.8 | 1,522.67

## Slide 14
Architectural:
 | Stone (m2) | Plaster (m2) | Paint (m2) | Brick (block) | Decoration (m2) | Tiles (m2)
B2 | 761 | 3,301 | 3,301 | 24,808 | 968 | 2,596
B1 | 531 | 2,441 | 2,441 | 20,220 | 1,064 | 2,121
GF | 856 | 2,885 | 2,885 | 23,240 | 1,123 | 2,080
Extras | 489 | 3,649 | 5,040 | 6,112 | - | 203
Total | 2,637 | 12,276 | 13,667 | 74,380 | 3,155 | 7,000

## Slide 15
Hand calculation.
  Footings:
  Volume of footing F8 = width * length * depth
  = 2.2 * 2.6 * 0.5 = 2.86
  Concrete volume from Revit = 2.86 m3
  Columns:
  Volume of columns C1 (0.9*0.4) = width * length * depth
  = 0.4 * 0.9 * 4.25 = 1.53
  Volume of column C1 from Revit =1.53

## Slide 16
3D- models.
Structural:

## Slide 17
Architectural :

## Slide 18
Lumion 8

## Slide 21: Primavera
Definition: It is a software used to plan and manage all kinds of complex projects while satisfying all requirements.
Benefits:
Better resources allocation.
Efficient progress tracking.
Analyze alternative plans.

## Slide 22
WBS.

## Slide 23
Activities Name and Relationships:

## Slide 24
Prepared data.
Productivity rates and Prices:

## Slide 25
Resources:

## Slide 26
Quantities:

## Slide 27
Activities’ Durations:

## Slide 28
Output data:
Total Duration:

## Slide 29
Gant Chart:

## Slide 30
Critical activities:

## Slide 31
S-curves:
The total budgeted cost is 5,763,775 NIS.

## Slide 32
Total labor cost is 1,178,330 NIS

## Slide 33
Total non-labor cost is 51,140 NIS

## Slide 34
Total material cost is 4,534,305 NIS

## Slide 35
Total labor count is 6508 budgeted labor unit.

## Slide 36
Total non-labor unit is 58 Machines

## Slide 37: NAVISWORKS
Definition: It is a comprehensive project review solution seeking powerful insight and predictability to improve productivity and quality.
Benefits:
Better visualization.
Clash detection.
Faster analyzation.

## Slide 38
Clash Detective.
Inputs:

## Slide 40
Output.

## Slide 41
Time Liner.
Inputs:

## Slide 44: Output

## Slide 45: Conclusions
In general, project management principles are not properly considered in the Palestinian construction sector. Furthermore, BIM techniques are rarely used or not used to the fullest.
Using Primavera, the total duration of the project is 208 workdays.
The estimated price in this project was 5,763,775 NIS. And after adding the OH and profit 6,916,530 NIS.
Most Revit quantities are higher than BOQ Higher accuracy and hand calculations are the proof.
The deviation in the prices was 496,991 NIS lower than the price estimated by the contractor.

## Slide 46
 | BOQ Data |  | Our Result | 
 | Quantity | Cost (NIS) | Quantity | Cost (NIS)
Excavation (m3) | 19,000 | 475,000 | 22,500 | 214,992
Exterior wall (m2) | 2,800 | 770,000 | 2,642 | 615,600
Interior wall (m2) | 4,250 | 393,250 | 4,383 | 185,650
plastering (m2) | 14,500 | 493,000 | 12,276 | 408,092
Tiles (m2) | 6,220 | 766,150 | 7,000 | 509,755
Paint (m2) | 11,450 | 245,500 | 13,667 | 93,931
Decoration (m2) | 1,060 | 105,300 | 3,155 | 358,770
Marble (m2) | 508 | 117,375 | 689 | 166,195
Blinding (m3) | 100 | 38,000 | 100.4 | 38,844
Footings total (m3) | 1135 | 800,600 | 1292.41 | 550,907
Outside walls footings (m3) | 370 | 307,100 | 398.38 | 340,848
Columns (m3) | 435 | 424,125 | 383.3 | 418,270
Outside walls (m3) | 530 | 509,500 | 545.59 | 557,400
Tie beams (m3) | 110 | 104,500 | 86.3 | 102,253
Slabs (m3) | 1312 | 1,127,500 | 1189.6 | 1,182,398
Door | 129 | 155,300 | 133 | 175,560
Curtain Wall + Aluminum Doors (m2) | 95 | 68,250 | 137 | 355,080
Aluminum work (m2) | 400 | 180,000 | 442 | 229,716
Steel Doors (m2) | 60 | 38,000 | 33 | 24,600
M2) window guard ( | 400 | 54,000 | 405 | 121,292
Handrails (m) | 60 | 15,000 | 48 | 16,230
Isoflex (m2) | 1825 | 82,125 | 2,000 | 145,080
NITOPROOF (m2) | 620 | 43,400 | 469 | 8,982
Exterior Stadium (m) | 130 | 39,000 | 115 | 34,538

## Slide 47: Recommendations
Focus on spreading project management principles.
Work on introducing the BIM concept to the Palestinian market in its correct forms and dynamics. By cooperating with several universities and unions.
Rely more on further detailing of the WBS and use inter-correlation between activities. This will facilitate having better time results for any project.
Continue the project by including the electrical and the mechanical models.

## Slide 48: THANK YOU ;)