## Slide 1: Quantity Surveying and Time Management for Faculty of Medicine-An-Najah National University
Prepared By:Ahmed Al-massri
Batool Sawafta
Lamya Hanani
Tariq Abatli
Supervied by:Eng. Reema Nassar

## Slide 2
Outline
Management Functions.
Project Constraints.
Project Delivery Systems.
Construction Contracts.
Methodology.
Quantity survey.
Rivet 3D modeling.
Time And Cost Management
using Primavera software.
Hand calculation.
Results And Conclusions.
Bill of Quantity.

## Slide 3: Management Functions:

## Slide 4: Project Constraints
Time
Cost
Quality

## Slide 5: Project Key Participant

## Slide 6: Project Delivery Systems
Traditional (Design-Bid-Build)
Design-Build (Turnkey)
Self-performance (Owner Builder)
Build Operate Transfer (BOT)

## Slide 7: Traditional (Design-Bid-Build)

## Slide 8: Design-Build (Turnkey)

## Slide 9: Self-Performance

## Slide 10: Build Operate Transfer (BOT)

## Slide 11: Construction Contracts
lump sum contracts or single fixed cost (عقد المبلغ المقطوع).
Unit price contract (عقد وحدة الأسعار).
Negotiated Cost plus fee contracts (عقد التفاوض).
Guaranteed maximum price (GMP)(عقد التكلفة مع ضمان حد أعلى للتكلفة).

## Slide 13: Methodology
This project is about quantity survey and cost estimate for a project of constructing.Faculty of medicine
The methodology of this project will be:
Studying the construction documents of the project.
Making a quantity survey using Revit program.
Estimating the time schedule for the project using Primavera.

## Slide 14: Quantity survey
The estimated quantities of materials required on a project.
It is determined by a professional surveyor or engineer
Net in place quantity & material quantity.

## Slide 15: Quantity Survey.
Data required for the preparation of an estimate or survey .
Drawings.
General and special conditions .
Rates and Specifications .

## Slide 16: Units of measure
The five basic categories of units used in estimating are:
Number
Length
Area
Volume
Weight

## Slide 17
About Project
Nablus (NNU)
6 Floors
6708m²

## Slide 18: ,

## Slide 19
Architectural Structural

## Slide 20
Levels

## Slide 21
Link CAD

## Slide 22
Sections Definition for the Structural Elements

## Slide 23
Foundation and tie beams

## Slide 24
  Reinforcing Draw Using Revit

## Slide 25
Internal Partition

## Slide 26
The Final result
Architectural Structural

## Slide 27
Tables from Revit

## Slide 29
Render

## Slide 31: lumion

## Slide 33: Primavera software

## Slide 34: Project definition

## Slide 37: Calendar Definition

## Slide 39: Currency Definition

## Slide 40: Activates Definition

## Slide 43: Resources definition
Definition

## Slide 45: Total Direct Cost and Working Days

## Slide 46: Calender Days

## Slide 47: S Curve

## Slide 48: Hand Calculations

## Slide 49
Concrete volume= length * width* high
= 0.4*0.6*3.7
=0.88m³.
In Revit the quantity of concrete equal 0.89m³, the percent of error 1.1% less than5%

## Slide 50
Weight of the bars = (Diameter²/162) (bar length) (# of bars)
Net Weight of the bars and stirrups=581 kg
In Revit the quantity of reinforcement equal 589 kg, the percent of error 1.5% less than 5%.

## Slide 51: Top view of B3

## Slide 52
Total area of tiles =1054.306 m²
In Revit the area of tiles equal 1059.58 m² , the percent of error 0.5% less than 5%.

## Slide 53: Results & Conclusions
The important results of our project :
Bill of Quantity
Total price of the project
Total duration of the project

## Slide 54: Bill of Quantity

## Slide 57
Mobilization= 0.02*2756750= 55135 $
Total Price=2811885 $

## Slide 58
Columns Shear Walls Cost and price.
Columns and Shear Walls cost = budgeted material cost+ labor cost= 395443$.
Indirect cost= waste material cost+ job and operating overhead cost.
Waste of materials= .05*(384619.8) = 19231$.
Total cost= 395443+19231=414674$.

## Slide 59
Job overhead = 414674*0.1= 41467 $. 414674+41467=456141 $.
Operating overhead=456141*0.05=22807$. 456141+22807=478948 $.
Profit =478948*0.15=71842 $. 478948+71842=550790 $.
Unit price for the columns and walls= Price/total volume. =550790/1354.5= 406.6$/ m

## Slide 60: Percentage of direct cost of some activities to total direct

## Slide 61: Results
The total project cost is 2189894 $.
The total project price is 2811885$
The project planning start at 16 August 2009, and the latest finish date 2nd of JAN 2011.
The duration for the project is 505 calendar days and 433 working day