## Slide 1: Claims in Construction Projects

## Slide 2: OUTLINE
*Introduction
*Methodology
*Data analysis
*Identifying the responsibility of causes of claims perception of contractors
*Rate of Importance perception of owners
*Identifying the responsibility of causes of claims perception of owners
*Rate of Importance perception of contractors
*Recommendations
*Case study

## Slide 3: Introduction
The aim of this research is to detect and analyze the factors that frequently cause claim in Nablus and Ramallah during the construction stage and allocation of causes .for issuing construction claims

## Slide 4: Methodology
The study will employ a questionnaire survey method. The data will be analyzed to identify the most important claims factors and identify the responsibility of causes of claims from the perspectives of the owners and contractors. Then recommendations about how to manage the will be suggested.

## Slide 5: Data analysis
Sample size:
SS = n'/ (1+ n'/N), n' = S² / V² = (0.5)² / (0.05)² = 100.
In Nablus:
SS. contractors = 100/(1+100/22) =18. SS. owner is assumed.
In Ramallah:
S. contractors = 100/ (1+100/24) =19. S SS. owner is assumed.
We fill out questionnaires through 37 buildings companies classified first class in Ramallah and Nablus (18 in Nablus and 19 in Ramallah)

## Slide 6: Causes of construction claims and identifying the responsible it is of each cause perception of contractors.
The owner is responsible for occurring the :claims are
.Late payments
.Differing site condition
.Design changes and Change in .specifications based on the owner request
Political reasons "wars" and force majeure.

## Slide 7
The contractor is responsible for occurring the claims are
Failure to provide access to the site .
.Poor management
.Insufficient qualified labor
.Delay
Poor understanding term of contract by the contractor.
Variation of brands.
Schedule error prepared by the contractor.

## Slide 8
And the others causes are responsible for designer:
Late approval for drawings and samples from .the supervisor engineer
Direct changes in the planned method of .construction
Delay in answering field questions and .variances
Design error or inconsistence (unclear) .drawings
Error in estimating the cost of the project, error .in estimating the duration of the project

## Slide 9: Rate of Importance perception of contractors
Scale | weight
4 | Extremely important
3 | Very important
2 | Important
1 | Somewhat important
0 | Not important
Weight of importance

## Slide 10: Top ten causes of claims perception of contractors
Rank | Cause | Weight from 4
1 | Extra work in site | 3.89
2 | Municipalities regulation for example forbidden entry of trucks Downtown from 8:00 am to 3:00pm. | 3.82
3 | Differing site condition. | 3.80
4 | Variation of brands (type is not available in market). | 3.76
5 | Delay in construction because of weather conditions. | 3.72
6 | Schedule error prepared by the contractor. | 3.70
7 | Currency change. | 3.68
8 | The difficulty of implementing the project, as a result of implementing the project for the first time. | 3.57
9 | Delay in answering field questions and variances. | 3.52
10 | Poor management of site conditions. | 3.46

## Slide 11: Causes of construction claims and identifying the responsible it is of each cause perception of owners
each cause perception of owners
The owner is responsible for occurring the claims are
.Late payments of agreed date
Design changes and change in specification based on the .owner request
.Variation of brands (type is not available in market)
.Force majeure
The contractor is responsible for occurring the claims are
.Failure to provide access to the site
.Poor management of site conditions
.Insufficient qualified labor in the site
.Delay

## Slide 12
And the others causes are because of the designer
late approval for drawings and samples .from the supervisor engineer
.Delay in answering field questions
Design error or (unclear) drawings.
.Error in estimating the cost and the .duration of the project
.Variation of brands

## Slide 13: Rate of Importance perception of owners
Rank | Cause | Weight from 4
1 | Late payment of agreed date. | 3.78
2 | Extra work in site. | 3.75
3 | Delay in construction because of weather conditions. | 3.69
4 | Differing site condition. | 3.65
5 | Delay in construction and completion of the work. | 3.60
6 | Poor management of site condition. | 3.52
7 | Failure to provide access to the site. | 3.48
8 | Planning error in the planning. | 3.44
9 | Poor performance in construction. | 3.41
10 | Interference with the contractor during construction. | 3.32

## Slide 14: Case study
Project name: Nablus - Beit Iba- Deir Sharaf road.
Funded by: USAID.
Construction management: BLACK&VETCH.
Contractor: APCO/ARCON.
Sub contractor: Brothers construction Company.

## Slide 15
The project is surfacing 2600 m from station 3000 m to 5600 m that is located on Nablus Deir Sharaf road.
For surfacing the street; Brothers Company concluded agreement with Qandeel .Company
Marshall test was examined in the lab, and .the results were positive
but after heavy rain on the street its color has became light nearby white, and there was crashing in the street.

## Slide 16
The lab was called again to examine the street, and took a sample 7*40*40 cm, the results of the test were as following:
Stiffness ratio= 470 mm/kg; and the minimum in the specification is 500 mm/kg.
There in the middle of the street section contains 300 m in good condition, but the lab recommended to remove it; because it will affect on the street.
Initially Qandeel rejected the recommendations. But After this; the disputes were resolved by negotiate.

## Slide 17: Briefly; in this case the claim was changes in the specifications that have been agreed, that the contractor is responsible for occurring, and the claim was resolved by negotiation.