## Slide 1: Quantity surveying for Muthalath Al Shuhada School
1

## Slide 2: Outlines
Introduction
GP1 Review
3D Model Utilizing Revit
Managing Project Using Primavira
Navisworks Software
Assessment
2

## Slide 3: Introduction
3
The construction sector is a very important economic sector in Palestine. It’s providing the necessary housing structures and economic activity.

## Slide 4: Introduction
  Study objective
Importance
  Limitation
4

## Slide 5: GP 1 Review
Muthalth Al- shuhadah school
located in Muthalth Al- shuhadah village
Which has a 2800 population
The school designed to contain about 200 students.
the school building contain 3 floors (453 for each)
5

## Slide 6: Building Information Modeling (BIM)
Definition
Importance
Uses of BIM
6

## Slide 7: Software Programs Used
7
Revit
Primavera
Navisworks

## Slide 8: 3D Model Utilizing Revit
8

## Slide 9: Architectural Model
9

## Slide 10: Insert CAD
10

## Slide 11: Site features
Select the optimum reduce level
Estimated the net cut/fill
11

## Slide 12: quantities result
12

## Slide 13: Architectural Wall
aid to protect the building from any external factors
improve the appearance form.
13
Interior walls

## Slide 14: Architectural Wall
14
External walls

## Slide 15: Architectural Wall
External wall Stone
15

## Slide 16: Doors
There are many shapes of doors
Can selecting particular proprieties of doors
16

## Slide 17: Windows
17
External windows
There are many shapes of Windows
Can selecting particular proprieties of Windows

## Slide 18: Windows
18
Internal windows

## Slide 19: Render
19

## Slide 20
Contain Structural Elements
Satisfy the SAFE of the Building
Structural model
20

## Slide 21: Grid System
Aid to ensure the boundaries of building
columns centerlines.
21

## Slide 22: Structural Walls
22
Walls that carrying the load (Load-bearing walls)
Ability to reinforced
part of shear walls

## Slide 23
23
Cross section in shear wall

## Slide 24: Footing
24
There are many different type of footing
Footing used in project:
Strip footing
Wall footing
Structural footing

## Slide 25
25
Cross section of footings

## Slide 26
26
Columns
Making the different type of columns.
Ability to reinforced
Columns used in project:
C1 30x50
C2 30x50
C3 30x70

## Slide 27
27
Columns types

## Slide 28
28
Beams
Making the different type of columns.
Ability to reinforced
Beams Details

## Slide 29
29

## Slide 30
Ground Beams and Neck Columns
30

## Slide 31
For more specified and sorting elements to achieve the exact quantities we are doing the following:
Ground Beams and neck columns
From manage bars >> Setting list >> project parameters
add new elements
31

## Slide 32
Ground Beams and neck columns
Then select the element and checked the parameter to take encounter
32

## Slide 33
33
Slabs
Slab used in the project:
Solid slab
One way Ribbed Slab
One way ribbed Slab

## Slide 34
34
Ribbed slab Section

## Slide 35
35
Stairs
Stairs Details

## Slide 36
Structural rebar used to reinforce all structural elements to enhance reality simulation.
36
Structural Rebar

## Slide 37
The main output that obtained from Revit is quantity surveying as shown:
37
Revit output

## Slide 38
38

## Slide 39
39

## Slide 40
40
MANAGING PROJECT USING PRIMAVERA

## Slide 41
41
Primavera Software
Objectives
Input
Output

## Slide 42
Enhance the management and controlling the project
Time schedule estimate
Budgeted cost estimate
Earned value analysis
Primavera Objectives
42

## Slide 43
43
Primavera input
Activity of project
Activity relation
Expenses

## Slide 44
44
Activity of project

## Slide 45
45
Activity Relation

## Slide 46
46
Activity Relation

## Slide 47
47
Expenses
.
      Expenses are the cost incurred in or required for something.
      Aid to facilitate and quickly estimation
      Expenses for site leveling

## Slide 48
the total cost was estimated for site leveling = 47650 + 86186 = 133838 ₪ as shown:
48
Expenses
Part of sheet excel estimation list

## Slide 49
Bar Chart
Time schedule
Budgeted cost
S-curve
Primavera Output
49

## Slide 50
Bart chart
50
Primavera Output

## Slide 51
Sec C-C
51
Primavera Output

## Slide 52
52
The total duration of project is 241 working days.
Time schedule
Primavera Output

## Slide 53
53
Primavera Output
      Budgeted Cost
The total budgeted cost of the project is 2,123,273 ₪

## Slide 54
Primavera Output
      S-Curve
54

## Slide 55
55
naviswork

## Slide 56
Navisworks Software
56
Objective
Input
Output
Navisworks Software

## Slide 57: Navisworks objective
Navisworks allows users to open and combine 3D models, navigate around them in real-time
Review the model using a set of tools including comments, redlining, viewpoint, measurements.
A selection of plug-ins enhances the package adding interference detection, 4D time simulation
57

## Slide 58: Navisworks Input
58

## Slide 59
59

## Slide 60
60
Navisworks Input

## Slide 61
Navisworks Output
61

## Slide 62
62

## Slide 63
63
ASSESSMENT
      A comparison has been achieved between the total cost and duration that estimated by the contractor and the budgeted total cost and duration that estimated by this study.
      .
      :
As shown above there was an over budget cost about 244,874 ₪

## Slide 64
64
ASSESSMENT
There was a delay of 125 working days which gives an indicator that the most important reason for the over budget occurred in the total budget cost during the executing of the project.